## Sheet1
| Description | Evaluation | Likelihood | Impact | Response | Control Measure
1 | Modifying completed coding | Can possibly break things or create new issues that become difficult to resolve | High | Medium | If done you can always use the undo method to revert changes | Either have a seperate copy on local machine that can be used as a safety net or create new brach soley for testing ideas and pull from that
2 | Incorrect Deletion | Lost of work | Medium | Medium | Find method to undo deletion | Rather than delete straight use comments to slowly phase the use of this folder out
3 | Requirements are not met as specified | App would not be perfect and may not perform as intended | Low | High | Try to adapt the features so they cover the specified taks | Always plan new features while referencing the specifications
4 | Unresolved issues | When problems arise in coding i.e. not function as inteneded and then being unable to resolve by yourself | High | Medium | Always reference your documents like the MoSCoW your acceptance critea and your tests so you have a clear end goal | By using the Test Driven Development methods you can ensure reductions in deviations during the project
5 | Uploading without fully testing | Bugs may cause the application to be faulty and possibly unusable | Low | High | Some errors can leak thorugh | When coding each function have the tests coded in parallel